## Overview Workpackages
| Focus a - Theory, systematic analysis and description | Focus b - Design and implementation
WP0 | Preliminary research and organisation
WP1 | Data collection and analysis | Analysis of ontological design
Participant interviews and observations
WP2 | Systematization of findings | Systematization of design approach
Expert interviews
WP3 | Theorization | Implementation
Foundational workshops with participants and experts
Prototyping of ontological propositions for voice assistants derived from workshops
WP4 | Evaluation, pubication and dissemination
Completion of the final research report (SNFS)
Dissemination of findings in lectures at international congresses and in peer-reviewed journals, as well as in an open-access guidlines for the future development of voice assistants as assistive technologies; publication of code base and blueprints in a git-based online-code repository

## Detailed Workpackages
| Focus a - Theory, systematic analysis and description | Focus b - Design and implementation
WP0 | Preliminary research and organisation
0.1 Approving research project by ethics comittee
0.2 Establishing collaborative network of partner institutions and actors
0.3 Survey on adoption and usage of voice assistants as assistive technologies
0.4 Sample workshops to test setup
M0: Q3 2024 Preparing research project, establishing research network and tryout workshop format as well as survey executed
WP1 | Data collection and analysis | Analysis of ontological design
| 1.1 Work with source material and review of literature | 1.1 Production of actor-network/ontology map of assistive technologies
| 1.2 Participant interviews | 1.2 Analysis and detailed description of tasks; conceptualization of user scenarios
| 1.3 Participatory observation | 1.3 Determination of design parameters on the basis of the criteria catalogue and the conceptualization and design approaches
1.4 Production of a catalogue of criteria and vocabulary for the description of assistive technologies
1.5 Analysis of voice assistants as assistive technologies
M1: Q4 2025 Work with sources, analysis and description of ATs, examination of user ontologies, relations, and interconnections concluded
M2: Q4 2025 determination of user scenarios and mapping of design ontology concluded
WP2 | Systematization of findings | Systematization of design approach
| 2.1 Identification and description of open issues | 2.1 Testing and evaluation of the technological feasability
M3: Q1 2026 detection of open issues in regards to research questions and goals concluded
M4: Q1 2026 evaluation of technologial feasability concluded
2.2 Expert interviews
| 2.3 Final evaluation of analyses | 2.3 Selection of an approach for the implementation of the prototypes
2.4 Systematic description of design ontology of assistive technologies
2.5 Final evaluation
M5: Q2 2026 final solution approach selected and evaluated
WP3 | Theorization | Implementation
3.1 Foundational workshops with participants and experts
3.2 Prototyping of ontological propositions for voice assistants derived from workshops
| 3.3 Final formulation of the results of the workshops and interviews, as well as of the evaluation | 3.3 Evaluation of the voice assistant prototypes
| 3.4 Final description of all parts of the dissertations | 3.4 Implementation of VA prototypes
3.5 Test of VA prototypes
3.6 Evaluation of VA Prototypes
M6: Q2 2027 workshops, evaluations of interviews and observations results formulated, dissertations completed
M7: Q2 2027 implementation, test and evaluation of prototypes concluded
WP4 | Evaluation, pubication and dissemination
4.1 Completion of the final research report (SNFS)
4.2 Dissemination of findings in lectures at international congresses and in peer-reviewed journals, as well as in an open-access guidlines for the future development of voice assistants as assistive technologies; publication of code base and blueprints in a git-based online-code repository
M8: Q4 2027 final research report, conference and exhibition concluded, dissemination of findings initiated
| 4.3 Completion of guidelines for the future design of participatory interfaces; consolidation of results | 4.4 Completion of models of assistive voice assistants; consolidation of results
4.4 Code documentation
M9: Q2 2028 design guidelines and code documentation concluded
M10: Q2 2028 design models of assistive voice assistant

## Timetable
|  | 2023 |  |  |  | 2024
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
WP0 | Preliminary research and organisation | bar: 2023 Q3 to 2024 Q2
Milestones | bar: 2024 Q2
|  | 2023 Q1: 2025; 2024 Q1: 2026 | 2027 |  |  |  | 2028
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
WP1 | Data collection and analysis | bar: 2025 Q1 to 2025 Q4
Analysis of ontological design | bar: 2025 Q1 to 2025 Q4
WP2 | Systematization of findings | bar: 2026 Q1 to 2026 Q2
Systematization of design approach | bar: 2026 Q1 to 2026 Q2
WP3 | Theorization | bar: 2026 Q3 to 2027 Q2
Implementation | bar: 2026 Q3 to 2027 Q2
WP4 | Evaluation, pubication and dissemination | bar: 2027 Q3 to 2028 Q2
| Milestones | 2025 Q4: M1 M2; 2026 Q1: M3 M4; 2026 Q2: M5; 2027 Q2: M6 M7; 2027 Q4: M8; 2028 Q2: M9 M10